## WBS & Gantt Chart
TIME CAPSULE FOR LOVERS — WBS & 12-WEEK GANTT CHART
Example schedule: 12 weeks ¦ Adjust start/end weeks and task durations to match your team's actual plan
WBS ID | Task Name | Level | Deliverable | Duration (Weeks) | Start Week | End Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.0 | Time Capsule for Lovers | 1 | Completed project and deployed prototype | 12 | 1 | 12
1.1 | Project Management | 2 | Project plan and management documents | 12 | 1 | 12
1.1.1 | Project Charter | 3 | Approved project charter | 1 | 1 | 1
1.1.2 | Project Plan & Schedule | 3 | Project plan and schedule | 1 | 1 | 2
1.1.3 | Risk Management Plan | 3 | Risk register and mitigation plan | 1 | 2 | 3
1.1.4 | Cost Management & Budgeting | 3 | Budget estimate and cost baseline | 1 | 2 | 3
1.1.5 | Stakeholder Communication | 3 | Communication plan and updates | 12 | 1 | 12
1.2 | System Analysis & Design | 2 | Requirements and design package | 4 | 1 | 4
1.2.1 | User Requirements & Stories | 3 | User stories and requirements | 2 | 1 | 2
1.2.2 | Functional & Non-Functional Requirements | 3 | Requirements specification | 1 | 2 | 3
1.2.3 | System Architecture Design | 3 | System architecture | 1 | 3 | 4
1.2.4 | Database Design | 3 | Database schema for capsules, users, triggers | 1 | 3 | 4
1.2.5 | UI/UX Wireframing & Design | 3 | Wireframes and UI mockups | 2 | 3 | 4
1.3 | Development & Integration | 2 | Integrated mobile app prototype | 6 | 5 | 10
1.3.1 | Frontend Development (Mobile App) | 3 | Mobile app screens and flows | 3 | 5 | 7
1.3.2 | Backend Development (APIs, Server) | 3 | Backend services and APIs | 4 | 5 | 8
1.3.3 | Database Implementation | 3 | Implemented database | 2 | 5 | 6
1.3.4 | Time Capsule Creation Functionality | 3 | Create, save and manage capsules | 2 | 6 | 7
1.3.5 | Trigger Logic & Messaging System | 3 | Event-based trigger and messaging logic | 3 | 7 | 9
1.3.6 | Capstone Integration | 3 | Integrated capstone build | 1 | 9 | 10
1.4 | Testing & QA | 2 | Tested and quality-checked application | 3 | 9 | 11
1.4.1 | Unit Testing | 3 | Unit test results | 1 | 9 | 9
1.4.2 | System Integration Testing | 3 | Integration test report | 1 | 10 | 10
1.4.3 | User Acceptance Testing (UAT) | 3 | Feedback from target users | 1 | 10 | 11
1.4.4 | Performance & Security Testing | 3 | Performance and security results | 1 | 11 | 11
1.5 | Deployment & Capstone Wrap-up | 2 | Final capstone deliverables | 2 | 11 | 12
1.5.1 | Final Capstone Documentation & Report | 3 | Final report and documentation | 2 | 11 | 12
1.5.2 | Project Presentation & Defense | 3 | Presentation and defense | 1 | 12 | 12
1.5.3 | App Store Deployment (Beta/Prototype) | 3 | Beta/prototype deployment package | 1 | 11 | 12
1.5.4 | Project Closure & Reflection | 3 | Lessons learned and closure | 1 | 12 | 12
Legend: colored bars show planned work weeks. Durations and timing are editable example estimates; task notes are attached as cell comments.
Note on B5: Notes: Project oversight across all phases
Note on B6: Notes: Ongoing
Note on B11: Notes: Ongoing
Note on B13: Notes: Lovers' needs; breakup triggers
Note on B23: Notes: Examples: low communication, SOS button
Note on B28: Notes: Students/staff feedback